## Portfolio_Risks_March_2026
Risk ID | Description | Impact Level | Probability | Mitigation Strategy | Owner | Last Updated
R-501 | API Latency Issues | High | Medium | Implement Redis caching | David L. | 2026-03-10
R-502 | Vendor Contract Delay | Medium | Low | Dual-source procurement | Sarah J. | 2026-03-12
R-503 | Skill Gap (GenAI) | High | High | Accelerated team training | Alex P. | 2026-03-14
R-504 | Budget Re-allocation | Low | Medium | Monthly variance review | Maya K. | 2026-03-15